## Transition Progress
Role Name | Actual GTS Activity Code | Deloitte Resource Name | Chargeback (Do Not Edit) | Monthly Cost for Resource | FY Cost for Resource | Original Plan | Original Planned Months | Original Plan Expense | Deloitte Resource Status | Actual Roll Off Date | Actual Months | Actual Expense | KT Begun | On or Off Shore | Vz GTS Resource | Comments
Einstein Reporting/Development | Business Activity/Resource | Zack Copman | Business (Edwards) | 34285 | 411424 | n/a - Business |  |  | Business
Functional Design | Business Activity/Resource | Allie Lafontant | Business (Edwards) | 34285 | 411424 | n/a - Business |  |  | Business
Functional Design | Business Activity/Resource | Sandesh Gavande | Business (Edwards) | 34285 | 411424 | n/a - Business |  |  | Business | [6 empty] | 4/22 (Cindy) Asha will bring Sandesh in the loop for KT from Sai to Bhaskara and Salmon
Functional Design | Business Activity/Resource | Clay Stanley | Business (Edwards) | 34285 | 411424 | n/a - Business |  |  | Business | 2020-06-19
Functional Design | Business Activity/Resource | Ester Ehindero | Business (Edwards) | 34285 | 411424 | n/a - Business |  |  | Business | 2020-08-31 | [5 empty] | Shardul Deshmukh's last day 2/28/2020 Esther Ehindero is BF under under Ernest Serrano
Functional Design | Business Activity/Resource | Trisha Ramakrishnan | Business (Liberto) | 34285 | 411424 | n/a - Business |  |  | Business
Leadership: Executive | Business Activity/Resource |  | Business (Edwards) | 11428.33 | 137140 |  |  |  | Business
Salesforce Technical Development | Business Activity/Resource | Abisek Pati | GTS (Sohoni) | 18026.67 | 216320 |  |  |  | Rolled Off | 2020-04-30 | 4 | 72106.68 |  |  |  | 03/20 We have 3 developers Onshore and 6 Developers Offshore. Can plan for KT to the Team from Abisek. 4/20 (Nicole) - Sweta, is pairing identified & KT scheduled 04/21( Sweta) - Per Magesh,Abishek is the Developer and DEV Team ( India, US) is already taking up this role. We dont need additional KT and can be planned for release
Program Management | Business Activity/Resource | Caroline Oles (Jenn is Filling In) | Business (Liberto) | 34285 | 411424 |  |  |  | Business | 2020-07-31
Salesforce Technical Development | Business Activity/Resource | Issam Awwad | Business (Edwards) | 18026.67 | 216320 | 2020-06-02 |  |  | Business - Rolled Off | 2020-03-20 |  |  |  | Eliminated |  | 3/20 - Issam Awwad (Developer) rolled off and Sai Krishna Gattoju moved to their role. Changed Sohoni to Edwards to track Lead developer, lead, PLanned KT to start on 03/25 "
Salesforce Technical Development | Detail Design & Build - 04A | Sai Krishna Gattoju | GTS (Sohoni) | 18026.67 | 216320 |  | 9 | 162240.03 | Rolled Off | 2020-05-29 | 5 | 90133.35 |  | Both | Bhaskara Nekkanti Salman Mohammed | 3/20 - Issam Awwad (Developer) rolled off and this person moved to their role. Changed UI Design to Tech Dev and Edwards to Sohoni Lead developer, lead, PLanned KT to start on 03/25 04/22 (Sweta) - Per Magesh, Sai to provide KT to Bhaskara/Salman ( We need to also include Sandesh). Asha to set the sessions by 04/27 5/11 (Cindy) Per Magesh email on 5/7 - since we rolled off all Deloitte Salesforce developers, I prefer to roll off Sai Gattoju by 05/29 and let Mythili roll off by 06/30 5/14 (Cindy)-spoke to Magesh, Sweta will confirm all KT complete on 5/15, roll off date will probalby change to 5/29 05/15(Sweta) - Roll-off Date planned as 05/29 based on below a) Gourav Gulati to take TA -100% b) Sreenivas to support 100% Prod Support c) Bhaskara to take up 50% TA and Lead activities from Sai d) New TA from Onshore - Poppy to add e) New DEV from Verizon India - Sweta to add
Manager: Technical Development | Detail Design & Build - 04A | Magesh Jayaraj | GTS (Sohoni) | 18026.67 | 216320 | 2020-06-02 | 6 | 108160.02 | Rolled Off | 2020-07-31 | 7 | 126186.69 | 2020-01-13 | On Shore | Tarkeshwari Maudgil | 6/22, Asha conf'd 7/3 target to roll off 6/23 (Cindy) target date to roll off is 7/31/20 7/28 (Nicole) - Cindy conf'd good and on target
Salesforce (SF) Technical Architecture Design | Detail Design & Build - 04A | Chirag Sanghvi | GTS (Sohoni) | 34285 | 411424 | 2020-06-02 | 6 | 205710 | Rolled Off | 2020-08-31 | 9 | 308565 |  | Onshore( Infosys SOW) | Charlie Bao | 4/20 (Nicole) - do we have TA to pair with? 04/21 (Sweta) - I will align someone here. ETA 04/25 04/22 (Sweta)- Per Magesh, We need strong Architect and arrive right technical solution to drive business . Looking forward for either US SOW or FTE to get this going, Since Business works in US time, we are looking for resources from US. 4/28 (Cindy) POC is looking for US candidate replacement as soon as a spot opens up 05/05 (Sweta) - Cindy is working with Infosys SOW to get a replacement @ Verizon US. Cindy has Rate card. 5/15 (cindy) Infosys still vetting candidates, no one has been determined yet 5/26 (cindy) Chirag will continue his activities until he can conduct KT when rplacement has been found 6/22 (Cindy) (Charlie) Juntao Bao is being onboarded on Infosys SOW, Start date will be July 1st maybe sooner. 7/2 - Asha confirmed roll off of end of Aug 7/10 (Cindy) still waiting for CR to be signed before Charlie can start 7/14/20 (Cindy0 Charlie Bao starts KT sessions to be scheduled 7/28 (Nicole) - Cindy will ensure Matt clear 7/28,(Cindy) sent email to Matt Fisher w clear last day message for Chirag for 8/31/20-Matt confirmed
Salesforce (SF) Technical Architecture Design | Detail Design & Build - 04A | Matt Fisher | GTS (Sohoni) | 34285 | 411424 | 2020-06-02 | 6 | 205710 | Roll Off Planned | 2020-09-30 | 9 | 308565 |  | Off Shore | Satya Vanga | 6/2, add dev lead and engage enterprise arch. for large activities/iniatives. 7/7 KT sessions being scheduled for Satya and Matt, Satya has reviewed trole documentation 7/10/20 1st session with Matt and Satya is 7/13/20 @ 9am eastern
Salesforce Technical Development | Detail Design & Build - 04A | Vaibhav Kudesia | GTS (Sohoni) | 18026.67 | 216320 | 2020-06-02 | 6 | 108160.02 | Rolled Off | 2020-04-30 | 4 | 72106.68 |  | Off Shore | Vijay S | Asha to set as 1:1 Currently in Reverse Shadowing phase, till 2/24 3/2 - Ready from March Sprint 3/20- Ready and roll off can be requested from Dev Perspective,except for Extra responsibilities Vaibahv now owns on Heroku 3/31 (Nicole) - Sweta to work on shifting Heroku activities so can roll off 4/20 (Nicole) - any update on resource for Heroku activities? 4/20 (Cindy) per Magesh Vaibhav was provding temp Heroku actiities while Sudha was on PTO, Sudha is now back so roll off of 4/30 can happen 0421 (Sweta) - We are good with Roll-off planned for 04/30
Salesforce Technical Development | Detail Design & Build - 04A | Prachi Phadnis | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-04-30 | 4 | 72106.68 |  | On Shore | Bhaskara Nekkanti | Bhaskara takes care of prod support, so being used for dev. 3/31 - Nicole - Sweta to talk to Magesh about rolling off since we have the dev focus. 04/01- Magesh to get back on the expedited date for Prachi 4/20 (Nicole) -is there an update on date or did he roll off on 4/17 as noted in roll off column? 4/20 (Cindy)per Poppy Bhaskara is doing support, Prachi can roll off on 4/30 0421 (Sweta) - We are good with Roll-off planned for 04/30 for prachi
Salesforce Technical Development | Detail Design & Build - 04A | Mythili Prem Kumar | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-06-30 | 6 | 108160.02 |  | Off Shore | Ajith G | Asha to set as 1:1 Currently in Reverse Shadowing phase, till 2/24 3/2 - Ready from March Sprint 3/20- Ready and roll off can be requested 04/03 - Mythili is working on TA responsibility, so roll-off needs to done once TA responsibiity is handed -off to Salman 4/20 (Nicole) - is Ajith or Salman taking over responsbilities? 4/20 Cindy checking with Sweta/Asha 0421 (Sweta) - Mythili and Salman are taking TA responsiblity equally. If we need mre TAs, then We need to start the KT next week after dicussion wth Magesh 4/24(Asha) : Gaurav would take up the TA role from Mythili,KT from mythili to be scheduled. 05/05 (Sweta) - Need to work with Magesh and ask him to schedule KT on TA activities from Mythili to Gaurav who reports to Poppy 5/11 (Cindy) Per Magesh email on 5/7- since we rolled off all Deloitte Salesforce developers, I prefer to roll off Sai Gattoju by 05/29 and let Mythili roll off by 06/30 - Mythili can provide tech leadership Sudhakar Nallamilli (Salesforce Admin/Release Management) and Sudha Duvvakula (Heroku) 5/15, ( Cindy) Vz Resources are overwhelmed due to telelsales migration and covid 19 Sweta is going to add new resource to offshore and use Srinivas for some of the work on prod support, per a meeting that Asha held on 5/15, Mythili's rolloff date has changed from 5/29 to 6/30 - Sweta to add more details about resolution for Mythli's and upcoming roll offs
Salesforce Technical Development | Detail Design & Build - 04A | Tommaso Massari | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-04-30 | 4 | 72106.68 | 2020-11-26 | Off Shore | Salman Mohammed | Salman will be 100% with March sprint 04/01 : Magesh to get back on Expedited Roll -off Date 4/20 (Nicole) -is there an update on date or is the one in actual column accurate? 4/20 Cindy checking with Sweta/Asha 0421 (Sweta) - We are good with Roll-off planned for 04/30
Salesforce Technical Development | Detail Design & Build - 04A | Trivi Kavuru | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-04-30 | 4 | 72106.68 | 2019-09-04 | On Shore | Ranjit Reddy | Poppy will remove Robert, making Ranjit 100% 04/03- Ranjit is already 100% 4/20 (Nicole) - if just 100% on 4/3 , are we still good with 4/30 roll off or need to push? 4/20 (Cindy) checking w Asha 0421 (Sweta) - We are good with Roll-off planned for 04/30
Salesforce Technical Development | Detail Design & Build - 04A | Vivek Sharma | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-01-01 | 0 | 0 | 2019-09-04 | Off Shore | Pallavi Ravishankar, | 3/1 - requested roll off as resource was never on SOW since it rolled to Nicole
Leadership: Executive | Business Activity/Resource | Julie Miller | Business (Liberto) | 11428.33 | 137140 |  |  |  | Rolled Off
Salesforce Technical Development | Detail Design & Build - 04A | Karthi Subramanian | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-03-20 | 3 | 54080.01 | 2020-01-13 | Off Shore | Asha James
Salesforce Technical Development | Detail Design & Build - 04A | Sudha Duvvakula | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Partial Shadowing | 2020-09-15 | 9 | 162240.03 | 2020-12-12 | Offshore/Onshore( Infosys SOW) | Umakant Suman/ Bala Swayam Pattanayak | Specialty is Heroku Difficulties in installing Heroku offshore. 3/20 - KT Complete and currently supporting Dev activities ,but have issues with Heroku not being enabled from VZ India Network 3/31 - Nicole, Sweta to look at adding an onshore in as well - so 2 replacing the one as Vaibhav also has Heroku activities 04/01 - Sweta/Asha need to check with Poppy if Bala is able to take up Heroku Messaging 4/20 (Nicole) - was owner identified or do we need to regroup on Heroku? 4/20 (Cindy) per Magesh Sudha was on PTO. but back working lead on Heroku -per Poppy, Bala can't get access to many Heroku activities, as well as Umakant 04/21 (Sweta) - We need Sudha as both Umakanth ( VzIndia) and Bala ( Vz US) dont have access to Heroku completely. 4/28 -(Per Sweta) Regarding Heroku, we don't have access and any activities related to Higher instances ( UAT & above), It's not possible to support from India . Umakant( VzIndia) will be 100% on Heroku dev and will support in DEV instances. 4/28 (Cindy) Bala does not have bandwidth 05/05 (Sweta) - Cindy is working with Infosys SOW to get a replacement @ Verizon US since Vz India doesnt have all Access for Heroku 5/6 (Cindy) Infosys POC looking for US candidates with skill sets obtained, using rate card for SF Dev 5/15 (cindy) Infosys still vetting candidates, no one has been determined yet 6/23 (Cindy) Swayam Pattanayak will start onboarding, Heroku Developer that will take Sudha's place, tentative start date is June 1st. 7/10 (Cindy) still waiting for CR to be signed before Swayam can start 7/15/20 - Infosys BF Swayam Pattanayak, working with help desk to log in to VPN 7/28 (Nicole) - Sweta will provide roll off date by EOW 7/28 (Sweta) - Release Date updated 08/31 8/12 (Sweta) - Release Date updated 09/15 9/1/20 Cindy sent Matt and Trisha a email letting them know Sudha's last day is 9/15
Release Management | Functionality Testing & Install 06A | Sudhakara Reddy | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Pending |  | 9 | 162240.03 |  | Onshore |  | 4/20 (Nicole) - Asha are any external tools still persent 4/21(Asha) - Gitlab and Code review tool Migration is still in discussion. Rest other tools we are good 05/05 (Sweta) - Release Management is basically on PROD and hence we need replacement at Verizon US. Cindy to check with Nicole on next plans 7/31/20 (Cindy)Swati can support consumer deployment provided consumer deployment and B2B deployment can be scheduled at two different times. Usually consumer deployments are done around 5 pm on Monday/Tuesday evening. B2B deployments are done at 6 am on Wednesdays. Swati to get a full KT from Sudhakar and document it. Once she documents it, she should do a reverse KT review with Sudhakar/Asha/Sweta. Ideally she should shadow Sudhakar on a ER deployment with Sudhakar being primary and she being secondary. Next time around they should reverse the role and Sudhakar should be secondary. Sweta / Asha needs to ensure Swathi is comfortable with all the consumer admin work before Sudhakar rolls off.
SIT | Functionality Testing & Install 06A | Pashine, Anshul Pashine | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-01-24 | 1 | 18026.67 | 2019-09-18 | On Shore | Swathi Kethineni | 1/13, Nicole requested roll off
SIT | Functionality Testing & Install 06A | Mohan Rajagopal | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-01-24 | 1 | 18026.67 | 2019-08-22 | Off Shore | Akshaya Ramakrishnan | 1/13, Nicole requested roll off
SIT | Functionality Testing & Install 06A | Bryan Farey | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-01-24 | 1 | 18026.67 | 2019-09-18 | On Shore | Mohana Pattapu | 1/13, Nicole requested roll off
SIT | Functionality Testing & Install 06A | Chris Somuah-Appianti (SIT) | GTS (Sohoni) | 18026.67 | 216320 | 2020-03-01 | 3 | 54080.01 | Rolled Off | 2020-03-20 | 3 | 54080.01 | 2019-12-02 | Off Shore | Bharath Myneni | Deloitte activities moved effective end of March spting
SIT | Functionality Testing & Install 06A | Jose Carampatan | GTS (Sohoni) | 18026.67 | 216320 | 2020-06-02 | 6 | 108160.02 | Rolled Off | 2020-03-06 | 3 | 54080.01 | 2019-08-22 | Both | Lavanya Koonala (50%) Divya Avirineni (50%) | Roll Off Requested - target 3/6
Manager: SIT | Functionality Testing & Install 06A | Svethlana Barthelot (Mgr) | GTS (Sohoni) | 18026.67 | 216320 | 2020-06-02 | 6 | 108160.02 | Rolled Off | 2020-03-31 | 3 | 54080.01 | 2020-01-13 | Both | Amarnath Chakka (Off) Poppy Javid (On) | Deloitte activities moved effective end of March spting
SIT | Functionality Testing & Install 06A | Rajani Karri (SIT/Dev) | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-03-06 | 3 | 54080.01 | 2020-12-02 | Off Shore | Shilpa Ravula [SIT] | Roll Off Requested - target 3/6
SIT | Functionality Testing & Install 06A | Senthil Kumar Malayalam | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-03-20 | 3 | 54080.01 | 2019-12-02 | Off Shore | Bharathi Jayachandran | Deloitte activities moved effective end of March spting
SIT | Functionality Testing & Install 06A | Bradlee Beetar | GTS (Sohoni) | 18026.67 | 216320 | 3 - Sept | 9 | 162240.03 | Rolled Off | 2020-03-20 | 3 | 54080.01 | 2019-12-02 | Off Shore | Ramakrishna Boini | Deloitte activities moved effective end of March spting
UI Design | Business Activity/Resource | Aneesha Ragireddy | Business (Liberto) | 18026.67 | 216320 |  |  |  | Business - Rolled Off | 2019-12-06 | 0 |  |  | Eliminated |  | Nicole -- resource left deloitte in Dec, no back fill was planned until Feb so ask not to be billed and not to backfill
UI Design | Business Activity/Resource | Sai Lakshmi Bolla | Business (Edwards) | 18026.67 | 216320 |  |  |  | Business - Rolled Off | 2020-03-20 | 3 |  |  | Eliminated |  | 3/20 - Nicole shifted activities and rolled off
Leadership: Executive | Manager |  | GTS (Sohoni) | 11428.33 | 137140 |  | 9 | 102854.97 | Rolled Off | Kris Tzankov rolled off 4/29 | 4 | 45713.32 |  | Both

## Pivot Table 2
100% |  | Estimated Annual Salary | Total Resources
400% | Onshore | needed | 0 | #VALUE!
1100% | Offshore | needed | 11 | #VALUE!

## Sheet9
VZ IT
Bhaskara
Srinivas
Gaurav
Salman
pallavi
Ajith
Ranjith
Henry
Umakant